## Slide 1: Tablet Pilot Findings
Milestone: Restaurant tablet pilot launched
How we got there...
Notes: Notes:
The tablet pilot launched at both locations
The weekend before we ran a successful test run at one location
Hard work of many team members over the course of a few months
Now, let’s take a look at how successful it was

## Slide 2: Evaluation
Did we achieve our goals?
Were customers satisfied?
In order to evaluate the tablet launch, we asked guests to complete a survey on the tablet at the end of their visit.
Notes: Notes:
We made a list of evaluation questions around how we wanted to measure success
It included questions around tablet experience, satisfaction, visit length, if they experienced any technical issues, and more
We administered the survey by offering it on the tablet after they pay

## Slide 3: Results
72%
of guests rated their experience as
either a 4 or 5 (Great)
Notes: Notes:
Guests were generally satisfied with their experience, but there’s room for improvement
Other results included:
Guests preferred their experience with the tablets over a traditional waiter experience
Guests found the checkout process quick
There’s still work to do on improving speed
Guest orders are still being made incorrectly

## Slide 4: Recommendation #1
Survey Finding: Table turn time didn’t decrease
Recommendation: Work with GMs on speeding up guest visits
Notes: Notes:
Guests noted that they were still waiting the usual time for their table
Guests noted that they were spending the same amount of time at the table
One goal for the tablets was to decrease visit time
We’ll work with the GMs to speed up visit time

## Slide 5: Recommendation #2
Survey Finding: Tablet malfunctions
Recommendation: Implement process for checking tablets before service/changing out tablets between guests
Notes: Notes:
Guests noted that some of their tablets weren’t working
We want to put a plan in place to check tablets at the beginning the night
We also want to put a plan in place to swap out tablets immediately if that happens